## Sprint 1
Automation Testing Case Study - 1
Following website is given for Automating Testing using Playwright Automation Page Factory/POM, Unit Testing
Url: http://redbus.in
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 (Manual Testing) | 1. Identify the Manual Test Conditiond that you want to automate. | 1. List of User Stories & Functions to test | Prompt | min 12 max 15
| 2. Create Manual Test Scenarios | 2. Test scenarios | Requirement analysis
| 3. Identify & Create the Manual Test Cases. | 3. Test Case design | Test plan, User Stories, test scenarios, test cases, execute, defect report, test summary report
| 2. Exceution of Test cases & reporting the defects for failures | 2. Defect reporting
| 3. Closure of the Manual project by creating Summary Report | 3. Traceability Matrix 4. Test summary report
Sprint Day 2 | 1. Identify the Manual Test Cases that you want to automate. |  |  | 3 to 4
| 2. Plan the flow of application that you want to test using automation test scripts. | 1. List of Test Cases(Excel) | Agents
| 3. Create a VS code project for performing Automation | 2. Creation of a Project | Skills
| 4. Install Playwright and its associated files |  | Prompt
5. Configure the project to perform End-to-End automation
| 6. Create a project structure (pages, data, testcases) | 3. Project Structure
| 7. Create Feature File (Scenario, Scenario Outline, Scenario Datatable) | 4. Creation of Feature File
| 7. Implement Page Object Model for Automtion. | 5. Creation of Pages
8. Ensure using all types of locators at least once
9. Ensure to follow good programming practices
10. Add Comments wherever required
| 11. Implementation of Step Definition File | 6. Creation of Step Definition
Sprint Day 3 | 1. Create a Utils where you can perform cross browser testing | 1. Creation of browser utils
| 2. Ensure you can perform testing with multiple browsers | 2. Creation of Step Definition
3. Creation of Step Definition
4. Use the pages to identify the elements which are stored
5. Ensure to handle all the interactions like Alert, Frames, Navigations, etc
Sprint Day 4 | 1. Use utils to call the browser
| 2. Convert one testcase with Data Driven Testing using Excel | 1. Completion of Data Driven Testing
| 3. Creation of PlayWright Reports along screenshots and videos | 2. Completion of Playwright Report
Sprint Day 5 | Sprint Review (Sprint Evaluation)